## Release T2 R2025.JUN Calendar
Line | Week number | Day/ Week/ Weekend | Start Date | End Date | Activity type | Activities | EAC | UTEST | PROD | FW | Other | Comments
1 | 2 | Weeks | 2024-01-08 | 2024-06-20 | Release scope | 4CB completes CR detailed assessments (including cross-service impact assessments where relevant)
2 | 27 | Day | 2024-07-02 | 2024-07-02 | Release scope | T2-WG proposes baseline release scope and STP
3 | 28 | Day | 2024-07-09 | 2024-07-09 | Release scope | Scope baseline & STP approved by the MIB
4 | 50 | Day | 2024-12-13 | 2024-12-13 | Documentation | Publication for non-binding XSDs in MyStandards and Readiness Portal in T2 open community | [5 empty] | 8 weeks before EAC deployment (OGPF)
5 | 5 | Day | 2025-01-29 | 2025-01-29 | Documentation | Publication for binding XSDs in MyStandards and Readiness Portal in T2 open community | [5 empty] | 9 business days before EAC deployment (OGPF)
6 | 6 | Day | 04/02/2025 | 04/02/2025 | Release scope | Publication date for draft Scope defining set of documents (CLM, RTGS, DWH, Common Components)
7 | 6 | Weekend | 2025-02-07 | 2025-02-07 | Release deployment | Deployment of Package 1 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
8 | 7 | Week | 2025-02-10 | 2025-04-14 | Release testing | T2 R2025.JUN release testing in EAC | E
9 | 8 | Weekend | 20/02/2025 | 20/02/2025 | Release deployment | Deployment of Package 2 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
10 | 10 | Weekend | 2025-03-07 | 2025-03-07 | Release deployment | Deployment of Package 3 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
11 | 11 | Day | 13/03/2025 | 13/03/2025 | Release scope | Latest publication date for updated Scope defining set of documents (CLM, RTGS, DWH, Common Components)
12 | 12 | Weekend | 2025-03-21 | 2025-03-21 | Release deployment | Deployment of Package 4 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
13 | 14 | Weekend | 2025-04-04 | 2025-04-04 | Release deployment | Deployment of Package 5 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
14 | 12 | Day | 2025-04-05 | 2025-04-05 | Documentation | Delivery of the T2 R2025.JUN Statement of IT Security (STITS) | [5 empty] | Delivery at the latest 10 weeks before PROD deployment
15 | 16 | Day | 2025-04-14 | 2025-04-14 | Documentation | Service Transition Status Report (STSR) for T2 R2025.JUN in Pre-Production (cut-off and delivery T2-WG)
16 | 16 | Day | 2025-04-15 | 2025-04-15 | Documentation | T2-WG/RMCG approval of the security assessment and STSR for T2 R2025.JUN in Pre-Production
17 | 16 | Day | 2025-04-15 | 2025-04-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2024.JUN to Pre-Production | [5 empty] | 8 business days before UTEST deployment
18 | 16 | Weekend | 2025-04-17 | 2025-04-17 | Release deployment | Deployment of Package 6 to EAC | E |  |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
19 | 16 | Day | 2025-04-19 | 2025-04-19 | Documentation | Delivery of T2 R2025.JUN CR Detailed Assessments to ECB Compliance Team for GDPR check | [5 empty] | This step is performed in view of the yearly reporting to the MIB in terms of GDPR by the ECB Compliance Team.
19 | 16 | Day | 2025-04-19 | 2025-04-19 | Documentation | Release risk assessment | [5 empty] | T2 Evolution and Operations teams are producing this assessment at the latest 8 weeks before PROD deployment
20 | 18 | Day | 2025-04-29 | 2025-04-29 | Release deployment | Deployment of Package 7 to EAC | E |  |  |  |  | RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
21 | 18 | Day | 2025-04-29 | 2025-04-29 | Release deployment | Start release deployment to Pre-production |  | U
22 | 18 | Day | 2025-04-29 | 2025-04-29 | Release deployment | Deployment of Package 1-7 to Pre-Production |  | U |  |  |  | Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
23 | 18 | Weeks | 2025-04-30 | 2025-04-30 | Release testing | Start of testing of T2 R2025.JUN scope elements in Pre-Production |  | U
24 | 18 | Week | 2025-04-30 | 2025-05-27 | Release testing | T2 R2025.JUN Release testing in Pre-Production |  | U
25 | 18 | Day | 2025-05-02 | 2025-05-02 | Release deployment | Deployment of Package 8 to EAC and Pre-Production | E | U |  |  |  | RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
26 | 18 | Day | 2025-05-03 | 2025-05-03 | Documentation | RMCG assessment of STITS | [5 empty] | Delivery 4 weeks after the STITS is delivered (OGPF)
27 | 19 | Day | 2025-05-08 | 2025-05-08 | Release deployment | Deployment of Package 9 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
28 | 20 | Day | 2025-05-16 | 2025-05-16 | Release deployment | Deployment of Package 10 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
29 | 21 | Day | 2025-05-23 | 2025-05-23 | Release deployment | Deployment of Package 11 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
30 | 22 | Day | 27/05/2025 | 27/05/2025 | Release testing | End of testing of T2 R2025.JUN scope elements in Pre-Production |  | U
31 | 22 | Day | 2025-05-27 | 2025-05-27 | Reporting | Service Transition Status Report (STSR) for T2 R2025.JUN in Production (cut-off and delivery to T2-WG)
32 | 22 | Day | 2025-05-28 | 2025-05-28 | Reporting | Delivery of the T2 R2025.JUN Information security assessment to RMCG
33 | 22 | Day | 2025-05-28 | 2025-05-28 | Reporting | T2-WG recommends the release deployment to Production | [5 empty] | 11 business days before PROD deployment (OGPF)
34 | 22 | Day | 2025-05-30 | 2025-05-30 | Release deployment | Deployment of Package 12 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
35 | 23 | Day | 2025-06-04 | 2025-06-04 | Reporting | MIB approves the release deployment to Production | [5 empty] | 8 business days before PROD deployment (OGPF)
36 | 23 | Day | 2025-06-06 | 2025-06-06 | Release deployment | Deployment of Package 13 to EAC and Pre-Production | E | U |  |  |  | Critical RD only. Proposed RN 7 business days before deployment. Final RN 2 business day before deployment.
37 | 24 | Weekend | 2025-06-14 | 2025-06-14 | Release deployment | Start release deployment to Production |  |  | P
Formulas:
Week number = WEEKNUM([Start Date])