## Release T2 R2026.NOV Calendar
Line | Week number | Start Date | End Date | Activity type | Activity Name | EAC | UTEST | PROD | Comments
1 | 48 | 2025-11-25 | 2025-11-25 | Release scope | T2-WG proposes baseline release scope and STP for T2 R2026.NOV
2 | 49 | 2025-12-02 | 2025-12-02 | Release scope | Scope baseline & STP for T2 R2026.NOV approved by the MIB
3 | 13 | 2026-03-25 | 2026-03-25 | Documentation | Delivery of non-binding XSDs in MyStandards for the T2-WG community and the market (T2 R2026.NOV)
4 | 31 | 2026-07-27 | 2026-07-27 | Documentation | Publication date for binding XSDs in MyStandards for the T2-WG community and the market (T2 R2026.NOV) |  |  |  | 9 business days before EAC deployment (OGPF)
5 | 32 | 2026-08-03 | 2026-08-03 | Documentation | Publication date for draft Scope defining set of documents (T2 and Common Components) related to T2 R2026.NOV
6 | 32 | 2026-08-07 | 2026-08-07 | Release deployment | T2 R2026.NOV deployment (Package 1) | E
7 | 38 | 2026-08-10 | 2026-09-14 | Release testing | T2 R2026.NOV release testing in EAC | E
8 | 34 | 2026-08-21 | 2026-08-21 | Release deployment | T2 R2026.NOV deployment (Package 2) | E
9 | 36 | 2026-09-03 | 2026-09-03 | Release deployment | T2 R2026.NOV deployment (Package 3) | E
10 | 37 | 2026-09-11 | 2026-09-11 | Release deployment | T2 R2026.NOV deployment (Package 4) | E
11 | 38 | 2026-09-14 | 2026-09-14 | Documentation | Latest publication date for updated Scope defining set of documents (T2 and Common Components) related to T2 R2026.NOV
12 | 38 | 2026-09-14 | 2026-09-14 | Reporting | Service Transition Status Report (STSR) for T2 R2026.NOV in Pre-Production (cut-off and delivery to T2-WG)
13 | 38 | 2026-09-14 | 2026-09-14 | Documentation | T2-WG/RMCG approval of the security assessment and STSR for T2 R2026.NOV in Pre-Production
14 | 38 | 2026-09-14 | 2026-09-14 | Documentation | Release risk assessment |  |  |  | T2 Evolution and Operations teams are producing this assessment at the latest 8 weeks before PROD deployment
15 | 38 | 2026-09-14 | 2026-09-14 | Documentation | Delivery of T2 R2026.NOV CR Detailed Assessments to ECB Compliance Team for GDPR check |  |  |  | This step is performed in view of the yearly reporting to the MIB in terms of GDPR by the ECB Compliance Team.
16 | 38 | 2026-09-15 | 2026-09-15 | Reporting | T2-WG Go / No-go decision to deploy T2 R2026.NOV to Pre-Production |  | U |  | 8 business days before UTEST deployment
17 | 38 | 2026-09-17 | 2026-09-17 | Release deployment | T2 R2026.NOV deployment (Package 5) | E
18 | 39 | 2026-09-24 | 2026-09-24 | Release deployment | Start release deployment to Pre-production |  | U
19 | 39 | 2026-09-24 | 2026-09-24 | Release deployment | T2 R2026.NOV deployment to Pre-Production (Packages 1-6) |  | U
20 | 44 | 2026-09-25 | 2026-10-28 | Release testing | T2 R2026.NOV release testing in UTEST |  | U
21 | 39 | 2026-09-25 | 2026-09-25 | Release deployment | T2 R2026.NOV deployment (Package 6) | E
22 | 40 | 2026-10-02 | 2026-10-02 | Release deployment | T2 R2026.NOV deployment (Package 7) | E | U |  | RD only
23 | 41 | 2026-10-09 | 2026-10-09 | Release deployment | T2 R2026.NOV deployment (Package 8) | E | U |  | RD only
24 | 42 | 2026-10-16 | 2026-10-16 | Release deployment | T2 R2026.NOV deployment (Package 9) | E | U |  | critical RD only
25 | 43 | 2026-10-23 | 2026-10-23 | Release deployment | T2 R2026.NOV deployment (Package 10) | E | U |  | critical RD only
26 | 44 | 2026-10-28 | 2026-10-28 | Release testing | End of testing of T2 R2026.NOV scope elements in Pre-Production
27 | 44 | 2026-10-28 | 2026-10-28 | Reporting | Delivery of the T2 R2026.NOV Information security assessment to RMCG
28 | 44 | 2026-10-28 | 2026-10-28 | Reporting | Service Transition Status Report (STSR) for T2 R2026.NOV in Production (cut-off and delivery to T2-WG)
29 | 44 | 2026-10-29 | 2026-10-29 | Reporting | T2-WG recommends the release deployment of T2 R2026.NOV to Production |  |  | P
30 | 44 | 2026-10-30 | 2026-10-30 | Release deployment | T2 R2026.NOV deployment (Package 11) | E | U |  | critical RD only
31 | 45 | 2026-11-04 | 2026-11-04 | Reporting | MIB approves the release deployment of T2 R2026.NOV to Production |  |  |  | 8 business days before PROD deployment (OGPF)
32 | 45 | 2026-11-06 | 2026-11-06 | Release deployment | T2 R2026.NOV deployment (Package 12) | E | U |  | critical RD only
33 | 46 | 2026-11-14 | 2026-11-14 | Release deployment | Start release deployment of T2 R2026.NOV to Production |  |  | P
Formulas:
Week number = WEEKNUM([End Date])