## CBT-UT Calendar
Week number | Start Date | End Date | Activity type | Activity Name | Pending agreement | UTEST | PROD | Comments
4 | 2026-01-21 | 2026-01-21 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 01-18 January
6 | 2026-02-04 | 2026-02-04 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 19-31 January
8 | 2026-02-18 | 2026-02-18 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-15 February
10 | 2026-03-04 | 2026-03-04 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 16-28 February
12 | 2026-03-18 | 2026-03-18 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-15 March
14 | 2026-03-30 | 2026-04-03 | Release deployment | R2026.JUN Deployment of TIPS Release R2026.JUN to UTEST |  | U
14 | 2026-03-30 | 2026-05-21 | Testing stage | R2026.JUN User Testing |  | U
15 | 2026-04-07 | 2026-04-07 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 16-31 March
17 | 2026-04-22 | 2026-04-22 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-19 April
19 | 2026-05-06 | 2026-05-06 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 20-30 April
21 | 2026-05-20 | 2026-05-20 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-17 May
23 | 2026-06-03 | 2026-06-03 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 18-31 May
25 | 2026-06-17 | 2026-06-17 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-14 June
27 | 2026-07-03 | 2026-07-03 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 15-30 June
30 | 2026-07-22 | 2026-07-22 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-19 July
32 | 2026-08-05 | 2026-08-05 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 20-31 July
34 | 2026-08-19 | 2026-08-19 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-16 August
36 | 2026-09-03 | 2026-09-03 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 17-31 August
38 | 2026-09-16 | 2026-09-16 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-13 September
41 | 2026-10-05 | 2026-10-05 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 13-30 September
43 | 2026-10-21 | 2026-10-21 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-18 October
45 | 2026-11-04 | 2026-11-04 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 19-31 October
47 | 2026-11-18 | 2026-11-18 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-15 November
49 | 2026-12-03 | 2026-12-03 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 16-30 November
51 | 2026-12-16 | 2026-12-16 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 1-13 December
2 | 2027-01-06 | 2027-01-06 | Special testing | BILL invoice for NCBs |  | U |  | Billing period 14-31 December