## ECMS R2026.JUN calendar
Start Date | End Date | Activity type | Activities | Comments
2025-07-31 | 2025-07-31 | Documentation | Publication for part 1 of non-binding XSDs in MyStandards and Readiness Portal
2025-08-14 | 2025-08-14 | Documentation | Publication for part 2 of non-binding XSDs in MyStandards and Readiness Portal
2025-11-24 | 2025-11-24 | Documentation | Publication for binding XSDs in MyStandards and Readiness Portal
2025-12-05 | 2025-12-07 | Release deployment | Package 1: deployment to EAC
2025-12-19 | 2025-12-21 | Release deployment | Package 2: deployment to EAC
2026-01-23 | 2026-01-25 | Release deployment | Package 3: deployment to EAC
2026-01-30 | 2026-02-01 | Release deployment | Package 4: deployment to EAC
2026-02-20 | 2026-02-22 | Release deployment | Package 5: deployment to EAC
2026-03-06 | 2026-03-08 | Release deployment | Package 6: deployment to EAC
2026-03-17 | 2026-03-17 | Decision | ECMS-WG go/no-go decision to deploy ECMS R2026.JUN to UTEST
2026-03-20 | 2026-03-22 | Release deployment | Package 7: deployment to EAC
2026-03-27 | 2026-03-29 | Release deployment | Packages 1-7: deployment to UTEST
2026-03-27 | 2026-03-29 | Release deployment | Package 8: deployment to EAC and UTEST
2026-04-17 | 2026-04-19 | Release deployment | Package 9: deployment to EAC and UTEST | RD only
2026-04-24 | 2026-04-26 | Release deployment | Package 10: deployment to EAC and UTEST | RD only
2026-04-30 | 2026-05-02 | Release deployment | Package 11: deployment to EAC and UTEST | Critical RD only
2026-05-07 | 2026-05-09 | Release deployment | Package 12: deployment to EAC and UTEST | Will not be used by the ECMS
2026-05-13 | 2026-05-15 | Release deployment | Package 13: deployment to EAC and UTEST | Critical RD only
2026-05-22 | 2026-05-24 | Release deployment | Package 14: deployment to EAC and UTEST
2026-05-29 | 2026-05-29 | Decision | ECMS-WG go/no-go decision to deploy ECMS R2026.JUN to PROD
2026-05-29 | 2026-05-31 | Release deployment | Package 15: deployment to EAC and UTEST
2026-06-03 | 2026-06-03 | Decision | MIB go/no-go decision to deploy ECMS R2026.JUN to PROD
2026-06-05 | 2026-06-05 | Release deployment | Package 16: deployment to EAC and UTEST | Critical RD only
2026-06-13 | 2026-06-15 | Release deployment | Start deployment to PROD
2025-11-22 | 2025-11-24 | Release deployment | Start deployment to PROD

## Counterparty-relevant CRs
Scope item reference | Title | Description | Planned EAC deployment package | Planned EAC deployment date
ECMS-0099-SYS | Alignment of ECMS messages with ISO maintenance release 2020–2024 | In line with the TARGET Services unfreeze strategy, all ECMS registered messages will be upgraded to ISO MR 2020-2024. For all base (ISO) messages that have been migrated to a higher version due to the ISO maintenance releases 2020-2024, there will be a version upgrade of ECMS customised messages in order to align the ECMS message versions with the ISO message versions. | R2026.JUN Package 1 | 2025-12-05
ECMS-0102-URD | Alignment of the ECMS with Eurosystem triparty policy | This change request will facilitate the cross-border use of triparty by ensuring that the correspondent central bank has access to the same level of information on triparty operations as the refinancing central bank. | R2026.JUN Package 3 | 2026-01-23
ECMS-0111-URD | Inclusion of a climate factor for the management of marketable assets | On 29 July 2025 the ECB announced the introduction of a climate factor in the Eurosystem’s collateral framework, to address financial risks related to climate change by protecting the Eurosystem against potential declines in the value of the collateral accepted in its refinancing operations, specifically in the event of adverse climate-related transition shocks. The climate factor covers individual marketable assets issued by non-financial corporations and their affiliated entities and may result in a reduction of the value the Eurosystem assigns to assets pledged as collateral - similar to a haircut. This change request will include the climate factor in the collateral value after haircut of marketable assets subject to the climate factor. | R2026.JUN Package 2 | 2025-12-19

## Counterparty-relevant PBIs
Problem ID | Description | Category | Planned EAC deployment package | Planned EAC deployment date
151230 | [APPR] MPO-Expected payment screen date filter and page size not working properly | ECMS.Application.Statements and reporting | R2026.JUN Package 2 | 2025-12-19
153163 | [Credit Claims] - CCMOB Failed with no- business validation errors and status not in the drop down search list - CAS preference with validity end date reached | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
155563 | The download button displayed when the search result is higher than 100.000, only downloads 10.000 | ECMS.Application.U2A screens | R2026.JUN Package to be confirmed
157814 | [APPR] CC-UHB-Display Credit Claim Instruction/Display Rating Instruction/Display Mobilisation instruction/Display Demobilisation Instruction | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
157963 | [APPR] ‘MPEC Reconciliation Report’ screen is not aligned with UHB | ECMS.Application.U2A screens | R2026.JUN Package 1 | 2025-12-05
159025 | [APPR] Manual valuation appears as modification reason instead of automatic valuation event in the pool postion history | ECMS.Application.Operational day | R2026.JUN Package 1 | 2025-12-05
159190 | Spelling mistakes in Search Screen and List Screen of “Confirm CC_ACC Eligibility” | ECMS.Application.U2A screens | R2026.JUN Package 1 | 2025-12-05
159473 | [EAC] CTPY with “Only margin call” cash collateral type link should be allowed to instruct cash collateral for its margin call value but taking into account the possible Relative Credit Limit haircut to the collateral value | ECMS.Application.Cash as collateral | R2026.JUN Package 1 | 2025-12-05
160127 | [APPR] BRRCRU36 impossible to trigger due to schema validation - Notification impact failed when CC file is received with unknown currency code- BRCCRU11 expected | ECMS.Application.Credit Claims | R2026.JUN Package 2 | 2025-12-19
160429 | ECMS fails schema validation for colr.xxx.creditclaimsfile | ECMS.Application.Credit Claims | R2026.JUN Package 2 | 2025-12-19
161628 | [APPR] CreditFreezing- receive camt.998 with unknown pool >> Camt.025 is being sent to the technical address of the NCB | ECMS.Application.Global credit and collateral position | R2026.JUN Package 2 | 2025-12-19
161836 | User modified in 4-eyes mode cannot be validated | ECMS.Application.Access Rights | R2026.JUN Package 1 | 2025-12-05
161839 | Sort results by ISIN is not working correctly | ECMS.Application.Billing | R2026.JUN Package 3 | 2026-01-23
163695 | Downloading (Export) more than 10k assets should be possible or displaying more than 10k assets | ECMS.Application.C2D/UC | R2026.JUN Package 3 | 2026-01-23
165112 | [APPR] Settled and Reimbursed report - Interest amount equal to 0 for Full reimbursed OMO | ECMS.Application.Statements and reporting | R2026.JUN Package 2 | 2025-12-19
166598 | [APPR] Two different alerts generated in case of margin call for the same pool at same time | ECMS.Application.Global credit and collateral position | R2026.JUN Package to be confirmed
166627 | [CBT] ACC changed to CC without any NCB/CTPY update - Eligibility rule"Minimum Threshold amount Domestic wrongly assessed case the credit Claim is Mobilised. | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
166715 | [APPR] Error when generating colr.016 message (Pool position report) | ECMS.Application.Pool Position and pool projection | R2026.JUN Package to be confirmed
166755 | GMC access should be removed from the roles #63, #23 and #24. | ECMS.Application.Access Rights | R2026.JUN Package 1 | 2025-12-05
170475 | [PROD] 4-eyes instruction able to be validated/rejected even though underlying instruction is in final status | ECMS.Application.U2A screens | R2026.JUN Package 4 | 2026-01-30
171107 | [PROD] Debtor rating not properly updated | ECMS.Application.Credit Claims | R2026.JUN Package 2 | 2025-12-19
171889 | [PROD] BRMOB20 not correctly applied when Rejection of the MOB via U2A | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
171949 | SoH not generated for accounts activated day(s) after its creation | ECMS.Application.Statements and reporting | R2026.JUN Package 2 | 2025-12-19
172213 | [PROD] An incorrect BBRR is applied when receiving a seev.031 for a non-existent ISIN | ECMS.Application.Corporate Actions | R2026.JUN Package 2 | 2025-12-19
172603 | Only official pdfs for CTPYs with MA positions are downloaded when clicking on All Official SOH. | ECMS.Application.Statements and reporting | R2026.JUN Package to be confirmed
173702 | [EAC] - Matching Credit Claims Files and Credit Line Updates - CCFile to Pool Movement , Pool Movement to Credit Line Instruction | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
173810 | [PROD] Seemt.002 Credit Claims - face amount inside the field “AvlblBal" is empty : “AvlblBal" should be filled with same value generated on the field "AggtBal". | ECMS.Application.Statements and reporting | R2026.JUN Package 4 | 2026-01-30
173878 | [AEAC] [DECB] Pool position report not purged | ECMS.Technical.Other | R2026.JUN Package 2 | 2025-12-19
173945 | Purging process of parties/accounts leads to failures in the message reception as the message subscription for these parties/accounts becomes corrupted | ECMS.Application.A2A interface | R2026.JUN Package 2 | 2025-12-19
174801 | Wrong 'Total Eligible Balance' in outgoing seev.036 | ECMS.Application.A2A interface | R2026.JUN Package 1 | 2025-12-05
174819 | For automatically generated SoH, the system is not including the field “BalAtSfkpgPlc” for ISIN issued in a different country | ECMS.Application.Statements and reporting | R2026.JUN Package 4 | 2026-01-30
178433 | “Interest rate” field on “Calculated Interest” functionality doesn’t include the “Spread” effect on the accrual calculation | ECMS.Application.OMO | R2026.JUN Package to be confirmed
178724 | Screens reporting Marketable Assests collateral shall display all ISINs with an actual asset position greater than zero. | ECMS.Application.Statements and reporting | R2026.JUN Package 1 | 2025-12-05
179081 | [EAC] Wrong Success message displayed in the Pop-up window when confirming CC Guarantee creation with 4 eyes principles | ECMS.Application.Credit Claims | R2026.JUN Package 1 | 2025-12-05
183625 | Excess ECL not aligned with SCL and ECL if Bundling activated | ECMS.Application.Global credit and collateral position | R2026.JUN Package 5 | 2026-02-20
183686 | MA value in the projection not consistent with expectation | ECMS.Application.Pool Position and pool projection | R2026.JUN Package 5 | 2026-02-20
185091 | Failure in outgoing seev.031 for CHAN when change type TERM or CERT | ECMS.Application.A2A interface | R2026.JUN Package 2 | 2025-12-19
185179 | Outgoing seev.035 not sent due to wrong message subscription setup | ECMS.Application.Message subscription | R2026.JUN Package 2 | 2025-12-19
185630 | CA status wrongly changed from "Notified" processing status to “Waiting payment” | ECMS.Application.U2A screens | R2026.JUN Package 2 | 2025-12-19